## Burndown Chart
Tasks | Initial Estimate | Week 1 | Week 2 | Week 3
Planned Hours | 28 | 14 | 14 | 14
User Story 1 | 2 | 1 | 0 | 1
User Story 2 | 2 | 1 | 0 | 1
User Story 3 | 1 | 0 | 0 | 1
User Story 4 | 1 | 0 | 0 | 1
User Story 5 | 1 | 0 | 0 | 1
User Story 6 | 1 | 0 | 0 | 1
User Story 7 | 1 | 0 | 0 | 1
User Story 8 | 2 | 1 | 0 | 1
User Story 9 | 2 | 0 | 0 | 1
User Story 10 | 2 | 0 | 0 | 0
User Story 11 | 4 | 0 | 0 | 0
User Story 12 | 2 | 0 | 0 | 0
User Story 13 | 4 | 0 | 0 | 0
User Story 14 | 4 | 0 | 0 | 0
Actual Hours | 0 | 3 | 0 | 9
Remaining Work | 29 | 26 | 26 | 17
Total | 29 | 3 | 0 | 9
Ideal Burndown | 29 | 15 | 1 | -13

## User Story Table of Contents
User Story Number | Week 2 User Stories |  | Team Member
1 | As a user, I want to register for an account by providing my first name, last name, sex, age, state, email address, username, and password, so that I can use the service. | 1 | Mike
2 | As a user, I want the registration form to use HTTP POST to a controller, so that my information is securely submitted. | 1 | Mike
3 | As a user, I want the server-side form validation to be performed, so that I can be sure that my information is valid and complete before submitting it. | 0 | Mike
4 | As a user, I want my registration information to be saved in a SQL Server relational database, so that I can easily access it later. | 0 | Mike
5 | As a user, I want to be forwarded to a success or error page after submitting the registration form, so that I can be informed whether my registration was successful or not. | 0 | Mike
6 | As a user, I want to log in to my account by providing my username and password, so that I can access my account. | 0 | Mike
7 | As a user, I want the login form to authenticate my information using the SQL Server database, so that my account is secure. | 0 | Mike
8 | As a user, I want to be forwarded to a success or error page after submitting the login form, so that I can be informed whether my login was successful or not. | 1 | Mike
9 | As a user, I want to be able to access the Login and Register functionality via the Main Menu, so that I can create an account and sign in to the application. | 2 | Mike
10 | As a user, I want to be able to see the game board after successfully logging into the application, so that I can start playing the game. | 2 | Mike
11 | As a user, I want the game board to have a visually pleasing design with properly scaled and arranged pieces, so that I can easily understand the game. | 4 | Mike
12 | As a user, I want to be able to click on a button on the game board and have the state of that button updated, so that I can interact with the game. | 2 | Mike
13 | As a user, I want the game logic to be implemented properly so that the game rules are followed correctly. | 4 | Mike
14 | As a user, I want the game buttons to be updated appropriately when I click on a button, so that I can see the game state change in real-time. | 4 | Mike

## Backlog
User Story
M2
As a user, I want to be able to see the game board after successfully logging into the application, so that I can start playing the game.
As a user, I want the game board to have a visually pleasing design with properly scaled and arranged pieces, so that I can easily understand the game.
As a user, I want to be able to click on a button on the game board and have the state of that button updated, so that I can interact with the game.
As a user, I want the game logic to be implemented properly so that the game rules are followed correctly.
As a user, I want the game buttons to be updated appropriately when I click on a button, so that I can see the game state change in real-time.