## Sheet1
User Story | Time Estimate (Hours) | Team Member | 2023-03-19 | 2023-03-20 | 2023-03-21 | 2023-03-22 | 2023-03-23 | 2023-03-24 | 2023-03-25 | 2023-03-26 | 2023-03-27 | 2023-03-28 | 2023-03-29 | 2023-03-30 | 2023-03-31 | 2023-04-01
As a new user, I want to register for an account so that I can access the website's features. | 2 | Michael | 2023-03-19: 2
As a registered user, I want to be able to log in to my account so that I can view and manage my profile information. | 2 | Michael | 2023-03-19: 2
As a registered user, I want to be able to update my profile information, such as my email address and password. | 4 | Michael | 2023-03-19: 4
As a registered user, I want to be able to delete my account if I no longer wish to use the website. | 2 | Michael | 2023-03-19: 2
As a system administrator, I want to be able to view a list of all registered users and their profile information for administrative purposes. | 4 | Michael | 2023-03-19: 4
As a registered user, I want to be able to recover my password if I forget it. | 3 | Michael | 2023-03-19: 3
As a registered user, I want to receive email notifications for important account-related events, such as password reset requests or account deletions. | 3 | Michael | 2023-03-19: 3
As a system administrator, I want to be able to manage user roles and permissions to control access to certain website features or content. | 8 | Michael | 2023-03-19: 8
Remaining work hours(deal) | 28 |  | 2023-03-19: 28
Remaining work hours(actual) | 28 |  | 2023-03-19: 28